## File 1
Project Name | Shoes Shop
Project Manager | Nguyễn Đình Bảo
Project Deliverable
Scope Statement
Start Date | 2018-04-03
End Date | 2018-05-22
Overall Progress | 20%
Task Name | Responsible | Start | End | Days | Status
Sprint 1 | Nguyễn Đình Bảo | 2018-04-03 | 2018-04-16 | 8 | In progress
Login | Nguyễn Xuân Toàn | 2018-04-03 | 2018-04-05 | 2 | In progress
Register | Nguyễn Xuân Toàn | 2018-04-05 | 2018-04-10 | 2 | Not started
Forget Password | Nguyễn Xuân Toàn | 2018-04-10 | 2018-04-12 | 2 | Not started
Personal Page(Not Logined) | Nguyễn Đình Bảo | 2018-04-03 | 2018-04-06 | 3 | In progress
Personal Page(Client) | Nguyễn Đình Bảo | 2018-04-09 | 2018-04-13 | 4 | Not started
Client Information | Nguyễn Đình Bảo | 2018-04-16 | 2018-04-17 | 1 | Not started
Cart | Vũ Đình Khánh | 2018-04-03 | 2018-04-06 | 3 | In progress
Selection to edit the products | Vũ Đình Khánh | 2018-04-09 | 2018-04-17 | 5 | Not started
Client Information(When client order) | Ngô Thành Sơn | 2018-04-03 | 2018-04-06 | 3 | In progress
Bill Detailed(Client) | Ngô Thành Sơn | 2018-04-09 | 2018-04-17 | 5 | Not started
Orders | Nguyễn Thanh Sang | 2018-04-03 | 2018-04-11 | 4 | In progress
Quantity Manage | Nguyễn Thanh Sang | 2018-04-11 | 2018-04-17 | 4 | Not started
Edit/Add Client Information | Lê Nguyễn Việt Thanh | 2018-04-03 | 2018-04-05 | 2 | In progress
Edit/Add Product Information | Lê Nguyễn Việt Thanh | 2018-04-05 | 2018-04-13 | 4 | Not started
Sprint 2 | Nguyễn Xuân Toàn | 2018-04-17 | 2018-05-03 | 8 | Not started
Show Product(Not Logined) | Nguyễn Xuân Toàn | 2018-04-17 | 2018-04-25 | 5 | Not started
Show Product(Logined by Client) | Nguyễn Xuân Toàn | 2018-04-26 | 2018-05-04 | 3 | Not started
Client Information | Nguyễn Đình Bảo | 2018-04-17 | 2018-04-18 | 1 | Not started
Personal Page(Shop) | Nguyễn Đình Bảo | 2018-04-18 | 2018-04-25 | 4 | Not started
Shop Information | Nguyễn Đình Bảo | 2018-04-26 | 2018-05-03 | 2 | Not started
Promotions | Vũ Đình Khánh | 2018-04-17 | 2018-04-25 | 5 | Not started
Promotions Information | Vũ Đình Khánh | 2018-04-26 | 2018-05-04 | 3 | Not started
Bill Detailed(Shop) | Ngô Thành Sơn | 2018-04-17 | 2018-04-25 | 5 | Not started
Notifications(Client) | Ngô Thành Sơn | 2018-04-26 | 2018-05-04 | 3 | Not started
Change Password | Nguyễn Thanh Sang | 2018-04-17 | 2018-04-20 | 3 | Not started
Transactions | Nguyễn Thanh Sang | 2018-04-23 | 2018-04-27 | 3 | Not started
Edit/Add Shop Information | Lê Nguyễn Việt Thanh | 2018-04-17 | 2018-04-25 | 5 | Not started
Edit/Add Promotions | Lê Nguyễn Việt Thanh | 2018-04-26 | 2018-05-04 | 3 | Not started
Sprint 3 | Ngô Thành Sơn | 2018-05-07 | 2018-05-17 | 8 | Not started
Show Product(Logined by Client) | Nguyễn Xuân Toàn | 2018-05-07 | 2018-05-09 | 2 | Not started
Rating by Client | Nguyễn Xuân Toàn | 2018-05-09 | 2018-05-11 | 2 | Not started
Notifications(Client) | Ngô Thành Sơn | 2018-05-07 | 2018-05-08 | 1 | Not started
Notifications(Shop) | Ngô Thành Sơn | 2018-05-08 | 2018-05-15 | 4 | Not started
Show Product(Shop) | Nguyễn Xuân Toàn | 2018-05-14 | 2018-05-18 | 4 | Not started

## File 2
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | X | X | High | Not Started | 83 | X
Login | X | X | Medium | Not Started | 2 | X
Register | X | X | Medium | Not Started | 2 | X
Forget Password | X | X | Medium | Not Started | 2 | X
Personal Page(Not Logined) | X | X | Medium | Not Started | 7 | X
Personal Page(Client) | X | X | Medium | Not Started | 5 | X
Client Information | X | X | Medium | Not Started | 4 | X
Cart | X | X | Medium | Not Started | 9 | X
Selection to edit the products | X | X | Medium | Not Started | 8 | X
Edit/Add Client Information | X | X | Low | Not Started | 5 | X
Bill Detailed(Client) | X | X | Low | Not Started | 8 | X
Orders | X | X | Medium | Not Started | 8 | X
Quantity Manage | X | X | Medium | Not Started | 8 | X
Edit/Add Client Information | X | X | Low | Not Started | 7 | X
Edit/Add Product Information | X | X | Medium | Not Started | 8 | X
Sprint 2 | X | X | High | Not Started | 90 | X
Show Product(Not Logined) | X | X | High | Not Started | 8 | X
Show Product(Logined by Client) | X | X | Medium | Not Started | 8 | X
Client Information | X | X | Medium | Not Started | 5 | X
Personal Page(Shop) | X | X | Medium | Not Started | 7 | X
Shop Information | X | X | Medium | Not Started | 7 | X
Promotions | X | X | Medium | Not Started | 8 | X
Promotions Information | X | X | Medium | Not Started | 8 | X
Bill Detailed(Shop) | X | X | Medium | Not Started | 8 | X
Notifications(Client) | X | X | Medium | Not Started | 8 | X
Change Password | X | X | Low | Not Started | 3 | X
Transactions | X | X | Low | Not Started | 4 | X
Edit/Add Shop Information | X | X | Medium | Not Started | 8 | X
Edit/Add Promotions | X | X | Medium | Not Started | 8 | X
Sprint 3 | X | X | High | Not Started | 33 | X
Show Product(Logined by Client) | X | X | Medium | Not Started | 5 | X
Rating by Client | X | X | Medium | Not Started | 7 | X
Notifications(Client) | X | X | Medium | Not Started | 8 | X
Notifications(Shop) | X | X | Medium | Not Started | 5 | X
Show Product(Shop) | X | X | Medium | Not Started | 8 | X

## File 3
Sprint Backlog Template
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
Login | 10
UI Design |  |  |  | 4 | 2 | 2 | 0 | 0 | 0 | 0
Code Feature |  |  |  | 6 | 0 | 3 | 3 | 0 | 0 | 0
Register | 10
UI Design |  |  |  | 4 | 2 | 2 | 0 | 0 | 0 | 0
Code Feature |  |  |  | 6 | 0 | 3 | 3 | 0 | 0 | 0
Forget Password | 10
UI Design |  |  |  | 4 | 2 | 2 | 0 | 0 | 0 | 0
Code Feature |  |  |  | 6 | 0 | 3 | 3 | 0 | 0 | 0
Personal Page(Not Logined) | 15
UI Design |  |  |  | 4 | 2 | 2 | 2 | 1 | 1 | 0
Code Feature |  |  |  | 11 | 3 | 3 | 3 | 2 | 0 | 0
Personal Page(Client) | 20
UI Design |  |  |  | 5 | 2 | 1 | 1 | 1 | 0 | 0
Code Feature |  |  |  | 15 | 5 | 3 | 3 | 2 | 0 | 0
Client Information | 10
UI Design |  |  |  | 4 | 0 | 0 | 2 | 2 | 0 | 0
Code Feature |  |  |  | 6 | 0 | 0 | 3 | 3 | 0 | 0
Cart | 15
UI Design |  |  |  | 5 | 2 | 3 | 0 | 0 | 0 | 0
Code Feature |  |  |  | 10 | 5 | 3 | 3 | 0 | 0 | 0
Edit/Add Client Information | 25
UI Design |  |  |  | 10 | 5 | 5 | 0 | 0 | 0 | 0
Code Feature |  |  |  | 15 | 5 | 5 | 5 | 0 | 0 | 0
Bill Detailed(Client) | 25
UI Design |  |  |  | 10 | 0 | 0 | 5 | 5 | 0 | 0
Code Feature |  |  |  | 15 | 0 | 0 | 5 | 5 | 5 | 0
Orders | 20
UI Design |  |  |  | 8 | 0 | 4 | 4 | 0 | 0 | 0
Code Feature |  |  |  | 12 | 0 | 3 | 3 | 3 | 3 | 0
Edit/Add Product Information | 20
UI Design |  |  |  | 4 | 0 | 2 | 2 | 0 | 0 | 0
Code Feature |  |  |  | 16 | 0 | 5 | 5 | 5 | 1 | 0
Show Product(Not Logined) | 25
UI Design |  |  |  | 10 | 5 | 5 | 0 | 0 | 0 | 0
Code Feature |  |  |  | 15 | 5 | 5 | 5 | 0 | 0 | 0
Show Product(Logined by Client) | 15
UI Design |  |  |  | 5 | 0 | 1 | 2 | 2 | 0 | 0
Code Feature |  |  |  | 10 | 0 | 3 | 2 | 1 | 5 | 0
Personal Page(Shop) | 20
UI Design |  |  |  | 4 | 0 | 2 | 2 | 0 | 0 | 0
Code Feature |  |  |  | 16 | 0 | 5 | 5 | 5 | 1 | 0
Shop Information | 10
UI Design |  |  |  | 4 | 2 | 2 | 0 | 0 | 0 | 0
Code Feature |  |  |  | 6 | 0 | 3 | 3 | 0 | 0 | 0
History Transaction | 15
UI Design |  |  |  | 4 | 2 | 2 | 2 | 1 | 1 | 0
Code Feature |  |  |  | 11 | 3 | 3 | 3 | 2 | 0 | 0
Promotions | 25
UI Design |  |  |  | 10 | 0 | 0 | 5 | 5 | 0 | 0
Code Feature |  |  |  | 15 | 0 | 0 | 5 | 5 | 5 | 0
Promotions Information | 15
UI Design |  |  |  | 4 | 2 | 2 | 2 | 1 | 1 | 0
Code Feature |  |  |  | 11 | 3 | 3 | 3 | 2 | 0 | 0
Bill Detailed(Shop) | 25
UI Design |  |  |  | 10 | 0 | 0 | 5 | 5 | 0 | 0
Code Feature |  |  |  | 15 | 0 | 0 | 5 | 5 | 5 | 0
Notifications(Client) | 20
UI Design |  |  |  | 8 | 0 | 0 | 4 | 4 | 0 | 0
Code Feature |  |  |  | 12 | 0 | 0 | 6 | 6 | 0 | 0
Change Password | 15
UI Design |  |  |  | 4 | 2 | 2 | 2 | 1 | 1 | 0
Code Feature |  |  |  | 11 | 3 | 3 | 3 | 2 | 0 | 0
Edit/Add Shop Information | 25
UI Design |  |  |  | 10 | 5 | 5 | 0 | 0 | 0 | 0
Code Feature |  |  |  | 15 | 5 | 5 | 5 | 0 | 0 | 0
Edit/Add Promotions | 15
UI Design |  |  |  | 4 | 2 | 2 | 2 | 1 | 1 | 0
Code Feature |  |  |  | 11 | 3 | 3 | 3 | 2 | 0 | 0
Show Product(Logined by Client) | 10
UI Design |  |  |  | 4 | 2 | 2 | 0 | 0 | 0 | 0
Code Feature |  |  |  | 6 | 0 | 3 | 3 | 0 | 0 | 0
Show Product(Shop) | 20
UI Design |  |  |  | 8 | 0 | 0 | 4 | 4 | 0 | 0
Code Feature |  |  |  | 12 | 0 | 0 | 6 | 6 | 0 | 0
Rating by Client | 10
UI Design |  |  |  | 4 | 2 | 2 | 0 | 0 | 0 | 0
Code Feature |  |  |  | 6 | 0 | 3 | 3 | 0 | 0 | 0
Total | 445 |  |  | 445 | 81 | 120 | 145 | 89 | 30 | 0

## File 4
Agile Release Plan
Sprint | Task | Start | End | Duration | Status | Release Date | Goal
1 | Login | 2018-04-03 | 2018-04-05 | 2 | Planned | 2018-04-05
1 | Registration | 2018-04-05 | 2018-04-10 | 2 | Planned | 2018-04-10
1 | Forget Password | 2018-04-10 | 2018-04-12 | 2 | Planned | 2018-04-12
1 | Personal Page(Not Logined) | 2018-04-03 | 2018-04-06 | 3 | Planned | 2018-04-06
1 | Personal Page(Client) | 2018-04-09 | 2018-04-13 | 4 | Planned | 2018-04-13
1 | Client Information | 2018-04-16 | 2018-04-17 | 1 | Planned | 2018-04-17
1 | Cart | 2018-04-03 | 2018-04-06 | 3 | Planned | 2018-04-06
1 | Selection to edit the products | 2018-04-09 | 2018-04-17 | 5 | Planned | 2018-04-17
1 | Edit/Add Client Information | 2018-04-03 | 2018-04-06 | 3 | Planned | 2018-04-06
1 | Bill Detailed(Client) | 2018-04-09 | 2018-04-17 | 5 | Planned | 2018-04-17
1 | Orders | 2018-04-03 | 2018-04-11 | 4 | Planned | 2018-04-11
1 | Quantity Manage | 2018-04-11 | 2018-04-17 | 4 | Planned | 2018-04-17
1 | Edit/Add Client Information | 2018-04-03 | 2018-04-05 | 2 | Planned | 2018-04-05
1 | Edit/Add Product Information | 2018-04-05 | 2018-04-13 | 4 | Planned | 2018-04-13
2 | Show Product(Not Logined) | 2018-04-17 | 2018-04-25 | 5 | Planned | 2018-04-25
2 | Show Product(Logined by Client) | 2018-04-26 | 2018-05-04 | 3 | Planned | 2018-05-04
2 | Client Information | 2018-04-17 | 2018-04-18 | 1 | Planned | 2018-04-18
2 | Personal Page(Shop) | 2018-04-18 | 2018-04-25 | 4 | Planned | 2018-04-25
2 | Shop Information | 2018-04-26 | 2018-05-03 | 2 | Planned | 2018-05-03
2 | Promotions | 2018-04-17 | 2018-04-25 | 5 | Planned | 2018-04-25
2 | Promotions Information | 2018-04-26 | 2018-05-04 | 3 | Planned | 2018-05-04
2 | Bill Detailed(Shop) | 2018-04-17 | 2018-04-25 | 5 | Planned | 2018-04-25
2 | Notifications(Client) | 2018-04-26 | 2018-05-04 | 3 | Planned | 2018-05-04
2 | Change Password | 2018-04-17 | 2018-04-20 | 3 | Planned | 2018-04-20
2 | Transactions | 2018-04-23 | 2018-04-27 | 3 | Planned | 2018-04-27
2 | Edit/Add Shop Information | 2018-04-17 | 2018-04-25 | 5 | Planned | 2018-04-25
2 | Edit/Add Promotions | 2018-04-26 | 2018-05-04 | 3 | Planned | 2018-05-04
3 | Show Product(Logined by Client) | 2018-05-07 | 2018-05-09 | 2 | Planned | 2018-05-09
3 | Rating by Client | 2018-05-09 | 2018-05-11 | 2 | Planned | 2018-05-11
3 | Notifications(Client) | 2018-05-07 | 2018-05-08 | 1 | Planned | 2018-05-08
3 | Notifications(Shop) | 2018-05-08 | 2018-05-15 | 4 | Planned | 2018-05-15
3 | Show Product(Shop) | 2018-05-14 | 2018-05-18 | 4 | Planned | 2018-05-18
Formulas:
Release Date = [End]